## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Bootstrap | No error message for duplicated UserID | High | 5 | 45 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | Bootstrap | No error message when user bids negative amount | High | 5
3 | 1 | Bootstrap | No error message if students bid for a course that has prerequisites that student has not completed | High | 5
4 | 1 | Bootstrap | Timetable clash error message does not show up for correct case. | High | 5
5 | 1 | Bootstrap | No error message for exam clash | High | 5
6 | 1 | Bootstrap | No error message if student bids more than 5 courses | High | 5
7 | 1 | Bootstrap | No error message if the student has not enough e-dollar to bid | High | 5
8 | 1 | Bid | Login successful and user is redirected to index.php. Correct name and current bids are shown on index.php. However, balance is wrong (should be $189 instead of $200 as ben has already bidded) | High | 5
9 | 1 | Bid | "Insufficient balance" error. User stays on same page. | High | 5
10 | 2 | Drop Bid | No error message for dropping a bid that was never bidded for | High | 5 | 108 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
11 | 2 | Drop Bid | No error message for dropping a bid that has already been dropped | High | 5
12 | 2 | Drop bid | No error message for dropping a bid with non-existent couse code | High | 5
13 | 2 | Drop Bid | No error message for dropping a bid with non-existent section | High | 5
14 | 2 | Drop Bid | No error message for dropping bid without writing Course Code and Section | High | 5
15 | 2 | Drop Bid | No error message for dropping bid without writing Course Code | High | 5
16 | 2 | Drop Bid | No error message for dropping bid without writing Section | High | 5
17 | 2 | Drop Bid | No error message for dropping bid with Course code ==" " and Secion == " " (white spaces) | High | 5
18 | 2 | Start round | When round is not set, there are error messages but does not affect functionalities. | Low | 1
19 | 2 | Round 1 | After bids are processed in round 1, if the user successfully bid, the edollar should remain the same but it added back the bidded amount. | High | 5
20 | 2 | Bootstrap | HTML chunk of text comes out on top of error messages. | Low | 1
21 | 2 | Bootstrap | gary.ng.2009 completed is103 (line 8 of course completeed.csv) although he did not complete IS102 yet. The error msg should be "invalid course completed", but it did not come out. | High | 5
22 | 2 | Bootstrap | gary.ng.2009 bids for IS203 and he has not completed the prereq of IS106, but there is no error for line 30 after the file has been imported.error message should be "incomplete prerequisites". | High | 5
23 | 3 | Bid | When user tries to update bid with an amount that is higher than his balance, the error shown is insufficient balance but the user initially bid gets deleted and edollar doesn’t get refunded. | High | 5 | 20 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
24 | 3 | End round | When round 2 is manually ended, round should be 2 and inactive but database status for round did not change | High | 5
25 | 3 | Round 2 | Student can bid for a course he/she is successful for. | High | 5
26 | 3 | Round 2 | Vacancy increases if someone drops a section that is bidded only in round 2 active. | High | 5
27 | 4 | Add bid | Student cannot bid for a course when the exam falls on the same day and time | High | 5 | 31 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
28 | 4 | Bootstrap | Should not be displayed in JSON format | High | 5
29 | 4 | Round 2 | Does not show the correct min bid for round 2 | High | 5
30 | 4 | Bootstrap | When bootstrapping an empty zipped file, there is a chunk of html text. | Low | 1
31 | 4 | Round 2 | Student cannot bid for a course he/she is successful for in round 1. | High | 5
32 | 4 | Bootstrap | In course.csv and section.csv, bootstrap does not give error when exam end time is in incorrect format | High | 5
33 | 4 | Bootstrap | In student.csv, no error message given when student has negative money. | High | 5
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Bootstrap | No error message for duplicated UserID | Resolved | 2019-10-01 | 2019-10-02 | JW & LT
2 | 1 | Bootstrap | No error message when user bids negative amount | Resolved | 2019-10-01 | 2019-10-02 | JW & LT
3 | 1 | Bootstrap | No error message if students bid for a course that has prerequisites that student has not completed | Resolved | 2019-10-01 | 2019-10-02 | JW & LT
4 | 1 | Bootstrap | Timetable clash error message does not show up for correct case. | Resolved | 2019-10-01 | 2019-10-02 | JW & LT
5 | 1 | Bootstrap | No error message for exam clash | Resolved | 2019-10-01 | 2019-10-02 | JW & LT
6 | 1 | Bootstrap | No error message if student bids more than 5 courses | Resolved | 2019-10-01 | 2019-10-02 | JW & LT
7 | 1 | Bootstrap | No error message if the student has not enough e-dollar to bid | Resolved | 2019-10-01 | 2019-10-02 | JW & LT
8 | 1 | Bid | Login successful and user is redirected to index.php. Correct name and current bids are shown on index.php. However, balance is wrong (should be $189 instead of $200 as ben has already bidded) | Resolved | 2019-10-01 | 2019-10-02 | JW & LT
9 | 1 | Bid | "Insufficient balance" error. User stays on same page. | Resolved | 2019-10-01 | 2019-10-02 | JW & LT
10 | 2 | Drop Bid | No error message for dropping a bid that was never bidded for | Resolved | 2019-10-05 | 2019-10-08 | LT & JY
11 | 2 | Drop Bid | No error message for dropping a bid that has already been dropped | Resolved | 2019-10-05 | 2019-10-08 | LT & JY
12 | 2 | Drop bid | No error message for dropping a bid with non-existent couse code | Resolved | 2019-10-05 | 2019-10-08 | LT & JY
13 | 2 | Drop Bid | No error message for dropping a bid with non-existent section | Resolved | 2019-10-05 | 2019-10-08 | LT & JY
14 | 2 | Drop Bid | No error message for dropping bid without writing Course Code and Section | Resolved | 2019-10-05 | 2019-10-08 | LT & JY
15 | 2 | Drop Bid | No error message for dropping bid without writing Course Code | Resolved | 2019-10-05 | 2019-10-08 | LT & JY
16 | 2 | Drop Bid | No error message for dropping bid without writing Section | Resolved | 2019-10-05 | 2019-10-08 | LT & JY
17 | 2 | Drop Bid | No error message for dropping bid with Course code ==" " and Secion == " " (white spaces) | Resolved | 2019-10-05 | 2019-10-08 | LT & JY
18 | 2 | Start round | When round is not set, there are error messages but does not affect functionalities. | Resolved | 2019-10-09 | 2019-10-09 | RL & JW
19 | 2 | Round 1 | After bids are processed in round 1, if the user successfully bid, the edollar should remain the same but it added back the bidded amount. | Resolved | 2019-10-14 | 2019-10-14 | LT & JY
20 | 2 | Bootstrap | HTML chunk of text comes out on top of error messages. | Resolved | 2019-10-16 | 2019-10-28 | JW & SJ
21 | 2 | Bootstrap | gary.ng.2009 completed is103 (line 8 of course completeed.csv) although he did not complete IS102 yet. The error msg should be "invalid course completed", but it did not come out. | Resolved | 2019-10-16 | 2019-10-28 | JW & SJ
22 | 2 | Bootstrap | gary.ng.2009 bids for IS203 and he has not completed the prereq of IS106, but there is no error for line 30 after the file has been imported.error message should be "incomplete prerequisites". | Resolved | 2019-10-16 | 2019-10-28 | JW & SJ
23 | 3 | Bid | When user tries to update bid with an amount that is higher than his balance, the error shown is insufficient balance but the user initially bid gets deleted and edollar doesn’t get refunded. | Resolved | 2019-10-25 | 2019-10-29 | JW & SJ
24 | 3 | End round | When round 2 is manually ended, round should be 2 and inactive but database status for round did not change | Resolved | 2019-10-25 | 2019-10-28 | JW & SJ
25 | 3 | Round 2 | Student can bid for a course he/she is successful for. | Resolved | 2019-10-29 | 2019-10-29 | JW & SJ
26 | 3 | Round 2 | Vacancy increases if someone drops a section that is bidded only in round 2 active. | Resolved | 2019-10-29 | 2019-10-29 | JW & SJ
27 | 4 | Add bid | Student cannot bid for a course when the exam falls on the same day and time | Resolved | 2019-10-31 | 2019-11-12 | JW & JY
28 | 4 | Bootstrap | Should not be displayed in JSON format | Resolved | 2019-10-31 | 2019-11-12 | JW & JY
29 | 4 | Round 2 | Does not show the correct min bid for round 2 | Resolved | 2019-10-31 | 2019-11-12 | JW & JY ¦ LT & SJ
30 | 4 | Bootstrap | When bootstrapping an empty zipped file, there is a chunk of html text. | Resolved | 2019-11-05 | 2019-11-05 | JW & JY
31 | 4 | Round 2 | Student cannot bid for a course he/she is successful for in round 1. | Resolved | 2019-11-07 | 2019-11-12 | LT & SJ
32 | 4 | Bootstrap | In course.csv and section.csv, bootstrap does not give error when exam end time is in incorrect format | Resolved | 2019-11-11 | 2019-11-12 | JW & JY
33 | 4 | Bootstrap | In student.csv, no error message given when student has negative money. | Resolved | 2019-11-11 | 2019-11-12 | LT & SJ