## Week 5
Person | Question | Week 5: 16/9/19 to 22/9/19
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jia Wei | What did you do yesterday? | Revising WAD | Code database | Inset data | Not a working day | Not a working day | Not a working day | Not a working day
| What will you do today? | Creating database | Insert data | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | Debugging the codes for creating database | Got bugs in inserting data | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
Sonia | What did you do yesterday? | Revising WAD | Code login | Insert data | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Login page | Insert data | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | Got bugs in inserting data | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
Jia Ying | What did you do yesterday? | Revising WAD | Code database | Insert data, Update schedule | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Organising schedule, creating database | Insert data, update schedule | Update schedule, Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | Got bugs in inserting data | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
Leon | What did you do yesterday? | Revising WAD | Code bootstrap | Insert data | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Creating bootstrap | Insert data | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | Got bugs in inserting data | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
Rachel | What did you do yesterday? | Revising WAD | Code login | Insert data | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Login page | Insert data | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | Got bugs in inserting data | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day

## Week 6
Person | Question | Week 6: 23/9/19 to 30/9/19
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jia Wei | What did you do yesterday? | Not a working day | Edited bootstrap | Edited bootstrap | Not a working day | Debugging | Edited bootstrap Add bid | Not a working day
| What will you do today? | Edited bootstrap | Edited bootstrap | Not a working day | Debugging | Edited bootstrap | Not a working day | Bootstrap
| Do you have any obstacles? | - | - | Not a working day | - | - | Not a working day | -
Sonia | What did you do yesterday? | Not a working day | Edited bootstrap | Edited bootstrap | Not a working day | Not a working day | Not a working day | UI, critical path
| What will you work on today? | Edited bootstrap | Edited bootstrap | Not a working day | Not a working day | Not a working day | UI, critical path | Testcase
| Do you have any obstacles? | - | - | Not a working day | Not a working day | Not a working day | - | -
Jia Ying | What did you do yesterday? | Not a working day | Partial help with coding | Partial help with coding | Not a working day | Not a working day | Not a working day | UI
| What will you work on today? | Partial help with coding | Partial help with coding | Not a working day | Not a working day | Not a working day | UI | Help out with add bid
| Do you have any obstacles? | - | - | Not a working day | Not a working day | Not a working day | - | -
Leon | What did you do yesterday? | Not a working day | Did bidding validations | Did bidding validations | Not a working day | Debugging | Edited bootstrap Add bid | Add bid
| What will you work on today? | Did bidding validations | Did bidding validations | Not a working day | Debugging | Edited bootstrap Add bid | Add Bid | Add bid
| Do you have any obstacles? | - | - | Not a working day | - | - | Not a working day | -
Rachel | What did you do yesterday? | Not a working day | Did bidding validations | Did bidding validations | Not a working day | Not a working day | Not a working day | Add bid
| What will you work on today? | Did bidding validations | Did bidding validations | Not a working day | Not a working day | Not a working day | Add Bid | Add bid
| Do you have any obstacles? | - | - | Not a working day | Not a working day | Not a working day | Not a working day | -

## Week 7
Person | Question | Week 7: 30/9/19 to 6/10/19
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jia Wei | What did you do yesterday? | Bootstrap | Bootstrap | PM Review | Debug | PM Review | Not a working day | Not a working day
| What will you do today? | Bootstrap | PM Review | Debug | PM Review | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Sonia | What did you do yesterday? | Testcases | JSON Drop Bid | PM Review | Testcases | PM Review | Not a working day | Not a working day
| What will you work on today? | JSON Drop Bid | PM Review | Testcases | PM Review | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Jia Ying | What did you do yesterday? | Help out with Add Bid | Help out with JSON | PM Review | Upload everything for PM review | PM Review | Not a working day | Updated testscases for dropbid, updated bm
| What will you work on today? | Help out with JSON | PM Review | Upload everything for PM review | PM Review | Not a working day | Updated testscases for dropbid, updated bm | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Leon | What did you do yesterday? | Add Bid | Bootstrap | PM Review | Debug | PM Review | Not a working day | Not a working day
| What will you work on today? | Bootstrap | PM Review | Debug | PM Review | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Rachel | What did you do yesterday? | Add Bid | JSON Drop Bid | PM Review | Check everything is correct for PM review | PM Review | Not a working day | Not a working day
| What will you work on today? | JSON Drop Bid | PM Review | Check everything is correct for PM review | PM Review | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week 8
Person | Question | Week 8: 7/10/19 to 13/10/19
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jia Wei | What did you do yesterday? | Not a working day | Not a working day | DB table for admin, admin functions | Not a working day | Start on JSON | Not a working day | Not a working day
| What will you do today? | Not a working day | DB table for admin, admin functions | Not a working day | Start on JSON | Not a working day | Round 2 clearing logic | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Sonia | What did you do yesterday? | Not a working day | Not a working day | Help either coding pair | Updating bug metrics | Clearing logic | Not a working day | Not a working day
| What will you work on today? | Not a working day | Help either coding pair | Updating bug metrics | Clearing logic | Not a working day | Not a working day | Updating testcases
| Do you have any obstacles? | - | - | - | - | - | - | -
Jia Ying | What did you do yesterday? | Not a working day | Not a working day | Clearing round 1 logic | add in database the round 1 fail | Clearing logic | Not a working day | Not a working day
| What will you work on today? | Not a working day | Clearing round 1 logic | add in database the round 1 fail | Clearing logic | Not a working day | Drop section , tidied up the add bid part for users | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Leon | What did you do yesterday? | Not a working day | Not a working day | Clearing round 1 logic | add in database the round 1 fail | Clearing logic | Not a working day | Not a working day
| What will you work on today? | Not a working day | Clearing round 1 logic | add in database the round 1 fail | Clearing logic | Not a working day | Drop section , tidied up the add bid part for users | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Rachel | What did you do yesterday? | Not a working day | Not a working day | DB table for admin, admin functions | Not a working day | Start on JSON | Not a working day | Not a working day
| What will you work on today? | Not a working day | DB table for admin, admin functions | Not a working day | Start on JSON | Not a working day | Round 2 clearing logic | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week 9
Person | Question | Week 9: 14/10/19 to 20/10/19
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jia Wei | What did you do yesterday? | Not a working day | Round 2 clearing logic JSON for add/update bid | Testing | Testing | Application Demo and Progress Update | Not a working day | Not a working day
| What will you do today? | Round 2 clearing logic JSON for add/update bid | Testing | Testing | Application Demo and Progress Update | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Sonia | What did you do yesterday? | Not a working day | Scheduling, testing, Week 9 slides | Complete slides and test | Testing and scheduling | Application Demo and Progress Update | Not a working day | Not a working day
| What will you work on today? | Scheduling, testing, Week 9 slides | Complete slides and test | Testing and scheduling | Application Demo and Progress Update | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | Need to come up with new test cases | Scheduling is timeconsuming and difficult to do properly without reviewing multiple times. | - | - | -
Jia Ying | What did you do yesterday? | Not a working day | Testing | Testing | Not a working day | Application Demo and Progress Update | Not a working day | Not a working day
| What will you work on today? | Testing | Testing | Not a working day | Application Demo and Progress Update | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Leon | What did you do yesterday? | Not a working day | Testing | Testing | Not a working day | Application Demo and Progress Update | Not a working day | Not a working day
| What will you work on today? | Testing | Testing | Not a working day | Application Demo and Progress Update | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Rachel | What did you do yesterday? | Not a working day | Round 2 clearing logic JSON for add/update bid | Testing | Not a working day | Application Demo and Progress Update | Not a working day | Not a working day
| What will you work on today? | Round 2 clearing logic JSON for add/update bid | Testing | Not a working day | Application Demo and Progress Update | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week 10
Person | Question | Week 10: 21/10/19 to 27/10/19
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jia Wei | What did you do yesterday? | Not a working day | Round 2 Clearing logic | Round 2 Clearing logic | Not a working day | Update JSON testcases, Testing for other functionalities | Not a working day | Not a working day
| What will you do today? | Round 2 Clearing logic | Round 2 Clearing logic | Not a working day | Update JSON testcases, Testing for other functionalities | Not a working day | Not a working day | Debugging JSON
| Do you have any obstacles? | - |  | - | - | - | - | -
Sonia | What did you do yesterday? | Not a working day | Round 2 Clearing logic | Round 2 Clearing logic, JSON web services | Not a working day | Update JSON testcases, Testing for other functionalities | Not a working day | Updated testcases
| What will you work on today? | Round 2 Clearing logic | Round 2 Clearing logic, JSON web services | Not a working day | Update JSON testcases, Testing for JSON | Not a working day | Updated testcases | Not a working day
| Do you have any obstacles? | - | how to get clearing amount for different scenarios | - | - | - | - | -
Jia Ying | What did you do yesterday? | Not a working day | JSON web services | JSON web services | JSON web services (dump) | Update JSON testcases, Testing for other functionalities | Not a working day | Updated testcases
| What will you work on today? | JSON web services | JSON web services | JSON web services (dump) | Update JSON testcases, Testing for JSON | Not a working day | Updated testcases | Debugging JSON
| Do you have any obstacles? | - | - | sorting of the bids | - | - | - | -
Leon | What did you do yesterday? | Not a working day | Scheduling, JSON web services,testing for other functionalities | JSON web services | Not a working day | Update JSON testcases, Testing for other functionalities | Not a working day | Updated testcases
| What will you work on today? | Scheduling, JSON web services,testing for other functionalities | JSON web services | Not a working day | Update JSON testcases, Testing for other functionalities | Not a working day | Updated testcases | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Rachel | What did you do yesterday? | Not a working day | JSON web services | Not a working day | JSON web services (dump) | Update JSON testcases, Testing for other functionalities | Not a working day | Not a working day
| What will you work on today? | JSON web services | Not a working day | JSON web services (dump) | Update JSON testcases, Testing for JSON | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | sorting of the bids | - | - | - | -

## Week 11
Person | Question | Week 11: 28/10/19 to 03/11/19
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jia Wei | What did you do yesterday? | Debugging JSON | Fixing bugs | Debugging Json, Debugging other functionalities | Debugging | Not a working day | Not a working day | Not a working day
| What will you do today? | Fixing bugs | Debugging Json, Debugging other functionalities | Debugging | Deploy to AWS, UAT, Debugging | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - |  | - | - | -
Sonia | What did you do yesterday? | Not a working day | Writing test cases, testing everything | Writing Testcases | Writing Testcases | Not a working day | Not a working day | Not a working day
| What will you work on today? | Writing test cases, testing everything | Writing Testcases | Writing Testcases | UAT , debugging | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - |  | - | - | -
Jia Ying | What did you do yesterday? | Debugging JSON | Writing authenticate, Json Dump | Json API testcases | Debugging | Not a working day | Not a working day | Not a working day
| What will you work on today? | Writing authenticate, Json Dump | Json API testcases | Debugging | UAT , debugging | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - |  | - | - | -
Leon | What did you do yesterday? | Not a working day | Json Dump, Update minutes & schedule | Json API testcases | Deploy to AWS, debugging | Not a working day | Not a working day | Not a working day
| What will you work on today? | Json Dump, Update minutes & schedule | Json API testcases | Deploy to AWS, debugging | Deploy to AWS, UAT, Debugging | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - |  | - | - | -
Rachel | What did you do yesterday? | Not a working day | Writing authenticate, Json Dump | Writing Testcases | Writing Testcases | Not a working day | Not a working day | Not a working day
| What will you work on today? | Writing authenticate, Json Dump | Writing Testcases | Writing Testcases | UAT , debugging | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - |  | - | - | -

## Week 12
Person | Question | Week 12: 4/11/19 to 10/11/19
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jia Wei | What did you do yesterday? | Not a working day | Fixing bugs gathered from UAT | Continue with bug fixes from UAT | Not a working day | Work on testcases and bug fixes | Continue to work on bugfixes (UI/Json) | Not a working day
| What will you do today? | Fixing bugs gathered from UAT | Continue with bug fixes from UAT | Not a working day | Work on testcases and bug fixes | Continue to work on bugfixes (UI/Json) | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Sonia | What did you do yesterday? | Not a working day | Work on bid status coding | Work on bid status coding (Round 2 logic) | Not a working day | Work on bid status coding (Round 2 logic), work on testcases | Work on testcases and bid status coding | Not a working day
| What will you work on today? | Work on bid status coding | Work on bid status coding (Round 2 logic) | Not a working day | Work on bid status coding (Round 2 logic), work on testcases | Work on testcases and bid status coding | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Jia Ying | What did you do yesterday? | Not a working day | Bug fixes, Work on automated testcases | Work on presentation slides, bug fixes | Not a working day | Work on testcases and bug fixes | Continue with bug fixes (UI/Json) | Not a working day
| What will you work on today? | Bug fixes, Work on automated testcases | Work on presentation slides, bug fixes | Not a working day | Work on testcases and bug fixes | Continue with bug fixes (UI/Json) | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Leon | What did you do yesterday? | Not a working day | Work on bid status coding | Work on bid status coding (Round 2 logic) | Not a working day | Work on bid status coding (Round 2 logic), work on testcases | Continue with bid status coding (min bid) | Not a working day
| What will you work on today? | Work on bid status coding | Work on bid status coding (Round 2 logic) | Not a working day | Work on bid status coding (Round 2 logic), work on testcases | Continue with bid status coding (min bid) | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -
Rachel | What did you do yesterday? | Not a working day | Update minutes & Schedule, work on automated test cases | Update minutes & Schedule, work on presentation slides, bug fixes | Not a working day | Update minutes & Schedule, work on testcases | Update Schedule, work on testcases, fix minor bugs (Json) | Not a working day
| What will you work on today? | Update minutes & Schedule, work on automated test cases | Update minutes & Schedule, work on presentation slides, bug fixes | Not a working day | Update minutes & Schedule, work on testcases | Update Schedule, work on testcases, fix minor bugs (Json) | Not a working day | Not a working day
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week 13
Person | Question | Week 12: 11/11/19 to 17/11/19
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jia Wei | What did you do yesterday? | Not a working day | Bug fixes for UI errors | Work on bugs noted from bug metrics | Not a working day | Finalised Manual Testcases, Commented on codes | Testing automated cases, commenting on codes | Deployment
| What will you do today? | Bug fixes for UI errors | Work on bugs noted from bug metrics | Not a working day | Finalised Manual Testcases, Commented on codes | Testing automated cases, commenting on codes | Depolyment | Preparing for Presentation
| Do you have any obstacles? | - | - | - | - | - | - | -
Sonia | What did you do yesterday? | Not a working day | Work on Manual bootstrap testcases, resolve last part for Bid status | Further work on Bid status (min bid) | Not a working day | Work on automated testcases | Added on additional automated test cases for round 2 bidding | Deployment
| What will you work on today? | Work on Manual bootstrap testcases, resolve last part for Bid status | Further work on Bid status (min bid) | Not a working day | Work on automated testcases | Added on additional automated test cases for round 2 bidding | Depolyment | Preparing for Presentation
| Do you have any obstacles? | - | - | - | - | - | - | -
Jia Ying | What did you do yesterday? | Not a working day | Bug fixes for UI errors , test booststrap automated | Work on bugs noted from bug metrics | Not a working day | Finalised Manual Testcases, Commented on codes | Testing automated cases, commenting on codes | Deployment
| What will you work on today? | Bug fixes for UI errors , test booststrap automated | Work on bugs noted from bug metrics | Not a working day | Finalised Manual Testcases, Commented on codes | Testing automated cases, commenting on codes | Depolyment | Preparing for Presentation
| Do you have any obstacles? | - | - | - | - | - | - | -
Leon | What did you do yesterday? | Not a working day | Resolve last part for Bid status | Further work on Bid status (min bid) | Not a working day | Work on automated testcases | Added on additional automated test cases for round 2 bidding | Deployment
| What will you work on today? | Resolve last part for Bid status | Further work on Bid status (min bid) | Not a working day | Work on automated testcases | Added on additional automated test cases for round 2 bidding | Depolyment | Preparing for Presentation
| Do you have any obstacles? | - | - | - | - | - | - | -
Rachel | What did you do yesterday? | Not a working day | Update minutes & Schedule, work on testcases | Update minutes & Schedule, work and supervise bug fixes, presentation slides | Not a working day | Update minutes & Schedule, presentation slides, work on automated testcases | Testing online version of BIOS , update schedule | Deployment
| What will you work on today? | Update minutes & Schedule, work on testcases | Update minutes & Schedule, work and supervise bug fixes, presentation slides | Not a working day | Update minutes & Schedule, presentation slides, work on automated testcases | Testing online version of BIOS , update schedule | Depolyment | Preparing for Presentation
| Do you have any obstacles? | - | - | - | - | - | - | -